## Ark1
Lofthus Frukt og Saft
| 1. week |  |  |  |  | 2. week |  |  |  |  | 3. week |  |  |  |  | 4. week
| 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13
Project Manager | Project management |  |  |  |  | Project management |  |  |  |  | Project management |  |  |  |  | Project management
Project Manager | Initial customer meeting |  |  |  |  | Customer meeting |  |  |  |  | Customer meeting | [5 empty] | Customer meeting Presentation
The Whole Team |  | Team meeting
The Whole Team |  | Researching/Planning
Designer |  | Research |  |  |  | Moodboard/Styletiles/Wireframes | [12 empty] | Finishing touches
The Whole Team |  |  |  |  | Team meeting Ideas Site planning | Team meeting |  |  |  | Team meeting | [6 empty] | Team meeting
Photographer | [6 empty] | Photoshooting/Editing |  |  |  | Photoshooting/Editing | [6 empty] | Finishing touches
Copywriter | [6 empty] | Text content development |  |  |  | Text content development | [6 empty] | Finishing touches
Front-End Developer | [6 empty] | Site outline/Site structure |  |  |  | Site build/Coding | [6 empty] | Finishing touches
Front-End Developer | [13 empty] | Coding/Testing |  | Coding/Testing
The Whole Team | [19 empty] | Launch